## Implementation Plan
Project Stage | Task Name | Resource Name | Start Date | Due Date | Task Status | Comment
Initiation Phase
| Coordinate to schedule Kick-Off client meeting | Dhana | 2023-08-30 | 2023-08-31 | Completed | Initiated meeting and reach out to client. Confirmed weekly meeting schedule. Introduced team. Project overview
| Coordinate with Client to get list of website to use for extraction | Dhana | 2023-09-06 | 2023-09-06 | Completed | Client provided 40 websites
| Review Project overview and Expectation | All
Planning Phase | Project Proposal Completion
| Define Project Goal | Veda | 2023-09-10 | 2023-09-10 | Completed
| Define Project Scope | Dhana | 2023-09-10 | 2023-09-10 | Completed
| Define Deleverables and Milestones | Angel | 2023-09-10 | 2023-09-10 | Completed
| Provide data specification per client requirement |  | 2023-09-11 | 2023-09-13 | Completed | Based on client requirement, please identify the data output specification
| Provide Work Breakdown Structures | Emily | 2023-09-10 | 2023-09-10 | Completed
| Review and Revise Proposal | All | 2023-09-11 | 2023-09-13 | Completed
| Internal Meeting to finalize Project Proposal | All | 2023-09-11 | 2023-09-13 | Completed
| Proposal Presentation | All | 2023-09-14 | 2023-09-20 | Completed
Execution Phase
| Identify and select 1 website to create code in Python | Development Team | 2023-09-12 | 2023-09-14 | Completed | During internal Teams meeting, we gonna evaluate and select the website for creating code in Python
| Understanding selected website | Development Team | 2023-09-12 | 2023-09-14 | Completed
7 | Create Scraping code | Kim | 2023-09-15 | 2023-09-21 | Completed
7+ | Create modularized code | Development Team | 2023-09-22 | 2023-09-26 | Completed
2-5days | Perform HTML or Other Parsing based on the defined website structure | Development Team | 2023-09-25 | 2023-09-27 | Completed
2-5days | Identify Data based on specification | Development Team | 2023-09-27 | 2023-09-29 | Completed
TBD | Scrape the assigned websites (20-25) | Development Team | 2023-09-27 | 2023-10-03 | Completed
5 | Create SQL table based on the extracted data | Emily/Martin/Angel | 2023-10-04 | 2023-10-09 | Completed | Database using MySQLWorkbench - for codes completed
| Testing for extracted data | Emily/Martin/Angel | 2023-10-03 | 2023-10-04 | Completed | Extracted data for completed codes. It matches the expected outcome
| Create initial table for selected website | Emily/Martin/Angel | 2023-10-08 | 2023-10-10 | Completed | For completed codes
| Join table | Emily/Martin/Angel | 2023-10-10 | 2023-10-15 | Completed | All completed codes (websites)
2 | Review | Emily/Martin/Angel | 2023-10-15 | 2023-10-17 | Completed | Everything is up to date - Database (MySQLWorkbench)
| Automation | Development Team | 2023-10-18 | 2023-10-24 | Completed
| Implement the functionality to schedule scraping | Development Team | 2023-10-25 | 2023-10-31 | Completed
| Enable automation for scraping task at predetermined intervals | Development Team | 2023-11-01 | 2023-11-07 | Completed
| Enable concurrent execution of multiple scraping tasks in parallel for enhanced efficiency. | Development Team | 2023-11-08 | 2023-11-13 | Completed
TBD | Incorporate mechanisms to tackle CAPTCHA challenges and facilitate IP rotation | Development Team | 2023-11-14 | 2023-11-25
TBD | Provide the capability to export the extracted data to various formats | Development Team | 2023-11-27 | 2023-11-28
Monitor Phase
| Keep Track of work progress | PM
| Meeting task deadlines | PM
| Communicate | PM
| Collaboration | PM
| Team Meeting | PM
Closing Phase
Oral Presentation 1
Peer Evaluation

## Gantt Chart
[7 empty] | 2023-08-30 | 2023-09-06 |  |  |  | 2023-10-04 |  |  |  | 2023-11-01 |  |  |  |  | 2023-12-06
| Project Start Date | 2023-08-30 |  |  |  |  | 2023-08-30 | 2023-09-06 |  |  |  | 2023-10-04 |  |  |  | 2023-11-01 |  |  |  |  | Dec
[5 empty] | Week starting: |  | 2023-08-30 | 2023-09-06 | 2023-09-13 | 2023-09-20 | 2023-09-27 | 2023-10-04 | 2023-10-11 | 2023-10-18 | 2023-10-25 | 2023-11-01 | 2023-11-08 | 2023-11-15 | 2023-11-22 | 2023-11-29 | 2023-12-06
| Project Name: | Website Scraping Tool with Python
# | Task | Assigned to | Start | End | Status | Comments
1 | Coordinate to schedule Kick-Off client meeting | Dhana | 2023-08-30 | 2023-08-31 | Complete
2 | Coordinate with Client to get list of website to use for extraction | Dhana | 2023-09-06 | 2023-09-06 | Complete
3 | Review Project overview and Expectation | All | 2023-09-06 | 2023-09-10 | Complete
4 | Define Project Goal | Veda | 2023-09-10 | 2023-09-10 | Complete
5 | Define Project Scope | Dhana | 2023-09-10 | 2023-09-10 | Complete
6 | Define Deleverables and Milestones | Angel | 2023-09-10 | 2023-09-10 | Complete
7 | Provide data specification per client requirement | Client | 2023-09-11 | 2023-09-13 | Complete
8 | Provide Work Breakdown Structures | Emily | 2023-09-10 | 2023-09-10 | Complete
9 | Review and Revise Proposal | All | 2023-09-11 | 2023-09-13 | Complete
10 | Internal Meeting to finalize Project Proposal | All | 2023-09-11 | 2023-09-13 | Complete
11 | Proposal Presentation | All | 2023-09-14 | 2023-09-20 | Complete
12 | Identify and select 1 website to create code in Python | Development Team | 2023-09-12 | 2023-09-14 | Complete
13 | Understanding selected website | Development Team | 2023-09-12 | 2023-09-14 | Complete
14 | Create Scraping code | Kim | 2023-09-15 | 2023-09-21 | Complete
15 | Create modularized code | Development Team | 2023-09-22 | 2023-09-26 | Complete
16 | Perform HTML or Other Parsing based on the defined website structure | Development Team | 2023-09-25 | 2023-09-27 | Complete
17 | Identify Data based on specification | Development Team | 2023-09-27 | 2023-09-29 | Complete
18 | Scrape the assigned websites (20) | Development Team | 2023-09-27 | 2023-10-03 | Complete
19 | Create SQL table based on the extracted data | Emily/Martin/Angel | 2023-10-04 | 2023-10-09 | Complete
20 | Testing for extracted data | Emily/Martin/Angel | 2023-10-03 | 2023-10-04 | Complete
21 | Create initial table for selected website | Emily/Martin/Angel | 2023-10-08 | 2023-10-10 | Complete
22 | Join table | Emily/Martin/Angel | 2023-10-11 | 2023-10-15 | Complete
23 | Export tables based on required format (CSV, Excel, Google Sheet) | Emily/Martin/Angel | 2023-10-15 | 2023-10-17 | Complete
24 | Automation | Development Team | 2023-10-18 | 2023-10-24 | Complete
25 | Implement the functionality to schedule scraping | Development Team | 2023-10-25 | 2023-10-31 | Complete
26 | Enable automation for scraping task at intervals as an input | Development Team | 2023-11-01 | 2023-11-07 | Complete
27 | Enable concurrent execution of multiple scraping tasks in parallel for enhanced efficiency. | Development Team | 2023-11-08 | 2023-11-13 | Complete
28 | Incorporate mechanisms to tackle CAPTCHA challenges and facilitate IP rotation | Development Team | 2023-11-14 | 2023-11-25 | Complete
29 | Provide the capability to export the extracted data to various formats | Development Team | 2023-11-27 | 2023-11-28 | Complete
Statuses
In-progress
Pending
Complete

## Team Members
Development Team | Project Admin Team
Hyungi Kim | Angel Li
Anastasia Mayangsari | Martin Navarro
Dhanashri Kanitkar | Vedavyas Chaturvedula
Vedavyas Chaturvedula | Emily Le
Pavan Kalyan Reddy